## Summary Action Items
Summary of CAFII Board and EOC Action Items
| Source | Action Item | Responsible | Deadline | Status Sept. 19, 2024
Association Strategy, Governance and Financial Management
1 | BOD: April 9, 2024 | At the June 4, 2024, Annual Meeting of Members, the final independent KPMG report of CAFII’s 2023 Audited Financial Statements will be presented for approval. | K. Martin | 2024-06-04 | Completed
2 | BOD: April 9, 2024 | CAFII’s 3-—to 5-year Strategic Plan will be included in the agenda for an upcoming EOC meeting, where the EOC will review, discuss, and provide feedback. | K. Martin | 2024-06-04 | Completed
3 | BOD: June 4, 2024 | After receiving EOC feedback and approval, CAFII’s 3-—to 5-year Strategic Plan will be presented to the Board at the upcoming October 8/24 BOD Meeting in Montreal, where the BOD will review, discuss, and approve the Plan. | K. Martin | 2024-10-08 | In Progress
4 | EOC: February 7, 2024 | Develop a strategic document around options for engaging with journalists, along with an assessment of each option's potential benefits and potential risks, to be presented at the next EOC meeting in March. | W. Bairos | 2024-03-26 | Completed
5 | EOC: March 26, 2024 | Present Media strategy options to the Board at the April 9/24 Board meeting with request for input and approval. | W. Bairos | 2024-04-09 | Completed
6 | BOD: June 4, 2024 | Produce an article for the Media Advocacy Committee and the EOC for review and input. | W. Bairos | 2024-09-19 | In Progress
7 | EOC: April 23, 2024 | Present the outcome of the Board presentation on the 2023 CAFII audit by KPMG at the Annual Meeting of Members on June 24, 2024. | K. Martin | 2024-06-04 | Completed
8 | EOC: April 23, 2024 | Present the outcome of the Board presentation on the 2023 CAFII audit by KPMG at the Annual Meeting of Members on June 24, 2024. | K. Martin | 2024-06-04 | Completed
9 | EOC: April 23, 2024 | Present the CAFII Succession Plan, with EOC feedback incorporated, to the Board at the June 4/24 Board Meeting for approval. | K. Martin | 2024-06-04 | Completed
Regulatory Initiatives
10 | BOD: April 9, 2024 | Request of the AMF a moratorium such that the cancellation due date for spousal insurance coverage of January 1/25 not be enforced | K. Martin | 2024 | Completed
11 | BOD: April 9, 2024 | The approach CAFII members are taking to dealing with multiple complaints regimes will be added to the agenda for the June 4, 2024, Board meeting. | K. Martin | 2024-06-04 | Completed
12 | EOC: June 25, 2024 | The EOC endorsed CAFII's setting up a virtual meeting with the BCFSA, to which the Market Conduct & Licensing Committee members and EOC members will be invited. | K. Martin | 2024 | Completed
13 | EOC: June 25, 2024 | : The EOC endorsed the Quebec/AMF Committee discussing the issue of the AMF publishing English documentation at the next committee meeting to determine the best course of action regarding harmonized translation and information sharing | K. Martin | 2024 | Completed
Association Operations
Research and Education; and Media Communications